## Blad1
Planning Milanov P3P |  |  |  | Jaartal : 2013
Onderdeel: |  |  |  | Week nr:
|  |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Aftrap | bar: Week nr: 6
Analyse | bar: Week nr: 6 to Week nr: 7
Tutorials bekijken
Design van de website/master pagina | bar: Week nr: 8 to Week nr: 14
Database aanmaken | bar: Week nr: 8 to Week nr: 14
Connectie database | bar: Week nr: 9 to Week nr: 14
CMS system | bar: Week nr: 10 to Week nr: 14
Category | bar: Week nr: 10 to Week nr: 14
Product | bar: Week nr: 10 to Week nr: 14
Type | bar: Week nr: 10 to Week nr: 14
User | bar: Week nr: 10 to Week nr: 14
Webshop | bar: Week nr: 10 to Week nr: 14
Betaling toevoegen | bar: Week nr: 12 to Week nr: 14
Login/register form | bar: Week nr: 10 to Week nr: 14
Admin pagina | bar: Week nr: 10 to Week nr: 14
Eerste demo | bar: Week nr: 11
Laatste demo | bar: Week nr: 13
Laatste versie | bar: Week nr: 14
Documentatie | bar: Week nr: 7 to Week nr: 14
|  | Ermee bezig |  | Week nr: 7: Uitloop; Week nr: 10: Perfectioneren
Taakverdeling
| Wat |  | Wie
| Analyse |  | Yme, Wouter, Niek
| Design FrontEnd |  | Yme, Wouter
| Design BackEnd |  | Niek
| Database aanmaken |  | Yme,Wouter
| Connectie database |  | Yme
| CMS Systeem |  | Yme,Wouter,Niek
| Category |  | Yme,Wouter
| Product |  | Yme,Wouter
| Type |  | Yme,Wouter,Niek
| User |  | Yme,Wouter,Niek
| Webshop |  | Yme,Wouter,Niek
| Betaling |  | Yme,Wouter
| Login/Register |  | Yme,Niek
| Admin pagina |  | Wouter
| Documentatie |  | Yme,Wouter,Niek