## Blad1
Planning Milanov P3P |  | Jaartal : 2013
Onderdeel: |  | Week nr:
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Aftrap | bar: Week nr: 6
Analyse | bar: Week nr: 6 to Week nr: 7
Tutorials bekijken
Design van de website/master pagina | bar: Week nr: 8 to Week nr: 14
Connectie database | bar: Week nr: 9 to Week nr: 14
CMS system | bar: Week nr: 10 to Week nr: 14
Webshop | bar: Week nr: 10 to Week nr: 14
Betaling toevoegen | bar: Week nr: 12 to Week nr: 14
Login/register form | bar: Week nr: 10 to Week nr: 14
Admin pagina | bar: Week nr: 10 to Week nr: 14
Eerste demo | bar: Week nr: 11
Laatste demo | bar: Week nr: 13
Laatste versie | bar: Week nr: 14
Documentatie | bar: Week nr: 7 to Week nr: 14
| Ermee bezig | Week nr: 7: Uitloop; Week nr: 10: Perfectioneren